RK-28-2007-17, př. 1

počet stran: 3

| Sixth Framework Programme Priority 2.5.8 Information Society Technologies | Promoting Ecosystems and Regional Development in support of Regional Operational Programming |
| --- | --- |

MEMORANDUM OF COLLABORATION WITH VYSOCINA Region (Project PHASE 2: June 2007 – August 2008)

# INTRODUCTION

The overall aim of the peardrop project is to evaluate and analyze; adapt and model; promote and exploit; and disseminate existing and evolving knowledge, evidence, systems and tools regarding regional innovation ecosystems and digital business ecosystems.

In particular, the main work of Phase 2 is to develop appropriate tools, systems and models to be used to plan the deployment of innovation ecosystems, business ecosystems, or digital business ecosystems in 12 regions: 4 partner regions – Aquitaine, Piemonte, Vysocina, Wales - and 8 other regions.

These 8 regions will be selected, inter alia, from the group of regions already collaborating with peardrop in Phase 1 and will be known  as the “associated regions”. The selection criteria used to select these 8 associated regions are the following:

- the level of the region’s interest in DBE

- achieving a good geographical balance

- regional readiness and clarity in DBE understanding

peardrop’s Phase 2 comprises three sub-phases:

- In the analysis and development sub-phase, each partner and associated region will develop systems, models and other tools to support the process of DBE planning and deployment. September 2007-November 2007

- The exploitation sub-phase is concerned with use of the aforementioned systems, models and other tools in following through the development of an actual regional DBE deployment plan with the partner and associated regions. December 2007-February 2008

- The third sub-phase deals with a process of reflection in which some validation of the systems, models and other tools is carried out. The aim is to try to understand retrospectively, in each of the regions, what happened, what worked and why, what did not work and why not. February 2008 – March 2008.

During Phase 2, 2 international stakeholder workshops will be organised. The first of these (Workshop 2, planned for February 7-8, 2008) will be for an invited audience only (from the partner and associated regions, from DBE cluster projects, and from the EC). Its main purpose will be to provide an opportunity for a thorough exchange of knowledge of experiences to enrich the understanding of the participants and of the processes being carried out.

The final international stakeholder workshop (Workshop 3) will take place at the end of the project and be open to both an invited set of delegates (those from Workshop 2) and to a wider (but limited) audience of interested participants. The aim will be to consolidate the team-work and community of interest already built up, to reach conclusions and policy recommendations regarding regional DBE deployment, to promote more widely the results and outputs of peardrop, and to debate and agree future steps and proposals for future research (regarding ERA and in FP7).

# CONSIDERING THAT

- EPMA – Agentura pro evropské projekty & management]

  - represents the peardrop Project in the Czech Republic as a peardrop contractor to eris@ (project coordinator)

  - is responsible for fulfillment of project tasks according to Description of Work

  - is also responsible for dissemination and promotion in the Czech Republic s well as in new member states of EU

- Vysocina Region (represented by Regional Authority)

  - represents the top regional policy maker in the field of regional development

  - provida the state aid for deveopment of innovative business, ICT adoption in SMEs in the region

  - cooperates with peardrop contractor in the Czech Republic

  - makes relevant decisions on behalf of setting the proper conditions for business development the Vysocina region

VYSOCINA REGION & peardrop

AGREE TO COLLABORATE ON

“THE DEVELOPMENT OF DBE SPECIFIC DEPLOYMENT TOOLS” &

ON “SPECIFIC DISSEMINATION” OF peardrop RESULTS

# In particular, during peardrop’s Phase 2 (June 2007 – August 2008)

- Vysocina Region agrees to:

- Contribute to the development of systems, models and other tools to support the process of DBE planning. September 2007-November 2007.

- Develop a DBE deployment plan for the Vysocina region December 2007-February 2008.

- Participate actively to the process of reflection in which some validation of the systems, models and other tools is carried out. February 2008 – March 2008.

- Share information on the DBE deployment plan evidence regarding business ecosystems at regional level, especially at Workshop 2 (foreseen for February 7-8th, 2008).

- Provide some feedback on the materials provided to Vysocina region by peardrop (answer to questionnaires, comment on specific documents…etc.).

- Participate at peardrop events, such as the 2 International Stakeholders Workshops (one planned for February 7-8th 2008 and the other one towards the end of the project. peardrop will cover the agreed travel and subsistence costs of participation – see specific paragraph below for details.

- Collaborate to promote & disseminate the findings of the peardrop project in each others’ events, promotion materials, specific regional publications, regional web sites, etc.

- peardrop will offer to Vysocina Region

- Key information & technical tools on innovative business paradigms already developed by other EU funded projects in an easy, clear and concise way

- Direct access to “Guides & Toolkits” being prepared by the Project: light, clear documents that will help finding the best methodology for deploying DBE and ICT business networking in Vysocina Region’s territory. In this way, Vysocina region will have the possibility to directly influence the preparation of the Project Guides & Toolkits (that should be ready by mid 2007).

- Support in the identification of barriers, in the anticipation of obstacles and in the development of possible solutions related to DBE deployment.

- Facilitations for the exchange information and experiences with a view to appreciating differences of approach taken in different regional contexts.

- A case study regarding the planning process for the region built upon the lessons learned in the process of development of a DBE deployment plan.

- To participate at peardrop events: valuable occasions to meet DBE specialists, other interested regions, and to discuss how to create a DBE deployment plan.

- Preferential access to support, help and expertise of specialists in the field.

- As for the COSTS incurred during the collaboration, EPMA will:

  - Through eris@, reimburse agreed travel and subsistence costs in full for 1 representative of Vysocina Region when attending each of the two peardrop International Stakeholders event (February 7-8th, 2008 and July-August 2008);

  - Any other cost will be covered by Vysocina region

# This memorandum of collaboration with the Vysocina Region has been discussed within the Regional Council meeting on October 2, 2007 and has been approved by the decision number of

# Jihlava, ………..of ………. 2007

In faith,

| Signature | Signature |
| --- | --- |
| Name and Last Name: Irina Zálišová | Name and Last Name: Jaroslav Hulák |
| Position: Director | Position: member of the Regional Council |
| Region: | Region: Vysocina |
| For EPMA: (peardrop contractor) | For Vysocina Region: (Partner region) |

# Footnotes

As stated in Article II.19.1.of the PEARDROP Contract with the EC, eligible costs incurred must be actual, economic and necessary for the participation to the Project.