## kraj
Summary Allocation Table | [13 empty] | RK-18-2010-45, př. 1upr1
Počet stran 1
Vysocina Regional Infrastructure (Finance Contract B)
Name of Operation:
Number of Operation: |  | 2006-0079
Financial table for all schemes (all in CZK)
Category A)
EIB Project number | Project identification | Name of project | Operational Programme | Priority | Measure | Total costs (CZK) |  | EU contribution (CZK) |  | Region's contribution (CZK) |  | Other resources (CZK) |  | Implementation Start of works End of works
(use numbering in chronological order) | (national system code) |  | (use abbreviations and/or numbering with explanatory notes below) |  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan Actual (DD/MM/YYYY) |  | Plan Actual (DD/MM/YYYY)
1 |  | Pavilón urgentní a intenzivní péče | ROP | 3. | 4. | 357500000 | - | 143000000 | - | 214500000 | - | 0 | - | 2011-01-01 | - | 2012-06-30 | -
2 | CZ.1.11/3.4.00/02.00599 | Pavilón pro matku a dítě | ROP | 3. | 4. | 327036000 | - | 107189000 | - | 219847000 | - | 0 | - | 06/05/2009 | - | 31/05/2011 | -
Category A - Total | [5 empty] | 684536000 | - | 250189000 | - | 434347000 | - | 0 | -
[9 empty] | of that EIB loan | 434347000 | -
Category B)
Project number | Project identification | Name of project | Investment programme (national / regional / other) |  |  | Total costs (CZK) |  | EU contribution (CZK) |  | Region's contribution (CZK) |  | Other resources (CZK) |  | Implementation Start of works End of works
(use numbering in chronological order) | (national system code) |  | (use abbreviations and with explanatory notes below) |  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan Actual (DD/MM/YYYY) |  | Plan Actual (DD/MM/YYYY)
3 |  | Gymnázium Chotěboř | regional budget |  |  | 82156635 | - | - | - | 82156635 | - | 0 | - | 10/08/2009 | - | 30/09/2010 | -
4 |  | SŠ řemesel a služeb MB | regional budget |  |  | 21950000 | - | - | - | 21950000 | - | 0 | - | 01/07/2010 | - | 15/12/2010 | -
5 |  | Rekonstrukce Helenín | regional budget |  |  | 165700000 | - | - | - | 165700000 | - | 0 | - | 05/2011 | - | 11/2012 | -
6 |  | III/03811 Havlíčkův Brod most ev. č. 03811-1 | regional budget |  |  | 28500000 | - | - | - | 28500000 | - | 0 | - | 19/04/2010 | - | 2010-10-30 | -
7 |  | II/344 Dolní Krupá | regional budget |  |  | 27610000 | - | - | - | 27610000 | - | 0 | - | 07/2010 | - | 06/2011 | -
Category B - Total | [5 empty] | 325916635 | - | - | - | 325916635 |  | 0
[9 empty] | of that EIB loan | 271597196 | -

## fiche
Summary Allocation Table
Name of Operation: |  | Vysocina Regional Infrastructure (Finance Contract B)
Number of Operation: |  | 2006-0079
Financial table for all schemes (all in CZK)
Category A)
EIB Project number | Project identification | Name of project | Operational Programme | Priority | Measure | Total costs (CZK) |  | EU contribution (CZK) |  | Region's contribution (CZK) |  | Other resources (CZK) |  | Implementation Start of works End of works |  |  |  | Project completed | EIA required | Natura 2000 | Public procurement
(use numbering in chronological order) | (national system code) |  | (use abbreviations and/or numbering with explanatory notes below) |  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan Actual (DD/MM/YYYY) |  | Plan Actual (DD/MM/YYYY) |  | (YES/NO) | (1) | (2) | (3)
1 |  | Pavilón urgentní a intenzivní péče | ROP | 3. | 4. | 357500000 | - | 143000000 | - | 214500000 | - | 0 | - | 2011-01-01 | - | 2012-06-30 | - | NO | NO | NO | E
2 | CZ.1.11/3.4.00/02.00599 | Pavilón pro matku a dítě | ROP | 3. | 4. | 327036000 | - | 107189000 | - | 219847000 | - | 0 | - | 06/05/2009 | - | 31/05/2011 | - | NO | NO | NO | E
Category A - Total | [5 empty] | 684536000 | - | 250189000 | - | 434347000 | - | 0 | -
[9 empty] | of that EIB loan | 434347000 | -
Category B)
Project number | Project identification | Name of project | Investment programme (national / regional / other) |  |  | Total costs (CZK) |  | EU contribution (CZK) |  | Region's contribution (CZK) |  | Other resources (CZK) |  | Implementation Start of works End of works |  |  |  | Project completed | EIA required | Natura 2000 | Public procurement
(use numbering in chronological order) | (national system code) |  | (use abbreviations and with explanatory notes below) |  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan Actual (DD/MM/YYYY) |  | Plan Actual (DD/MM/YYYY) |  | (YES/NO) | (1) | (2) | (3)
3 |  | Gymnázium Chotěboř | regional development plan |  |  | 82156635 | - | - | - | 82156635 | - | 0 | - | 10/08/2009 | - | 30/09/2010 | - | NO | NO | NO | N
4 |  | SŠ řemesel a služeb MB | regional development plan |  |  | 21950000 | - | - | - | 21950000 | - | 0 | - | 01/07/2010 | - | 15/12/2010 | - | NO | NO | NO | N
5 |  | Rekonstrukce Helenín | regional development plan |  |  | 165700000 | - | - | - | 165700000 | - | 0 | - | 05/2011 | - | 11/2012 | - | NO | NO | NO | N
6 |  | III/03811 Havlíčkův Brod most ev. č. 03811-1 | regional development plan |  |  | 28500000 | - | - | - | 28500000 | - | 0 | - | 19/04/2010 | - | 2010-10-30 | - | NO | NO | NO | N
7 |  | II/344 Dolní Krupá | regional development plan |  |  | 27610000 | - | - | - | 27610000 | - | 0 | - | 07/2010 | - | 06/2011 | - | NO | NO | NO | N
Category B - Total | [5 empty] | 325916635 | - | - | - | 325916635 |  | 0
[9 empty] | of that EIB loan | 271597196 | -
Responsible person (name): |  | ………………………….
Signature: |  | ………………………….
Date: |  | DD/MM/YYYY
Explanatory notes:
1 | Yes/No: write Yes if the project is subject to an Environmental Impact Assessment (EIA) or Strategical Environmental Assessment (SEA); EIA Directive: 85/337/EEC, 97/11/EC, 2003/35/EC (see the National and Regional law transposition) and SEA Directive: 2001/42/EC (in case of a yes answer, please give summary details).
2 | Yes/No: Yes if the project is located in a natural reserve area (current or planned) or in area subject to specific environmental limits. Please complete Form A (in case of no impact, could be based on a list of schemes) or Form B (in case of significant impact).
3 | “I”: International Tender Procedure; "E": European Tender"; “N”: National Tender; “Ne”: Negotiation Procedures; “D”: Direct attribution; “Em”: Emergency procedure; “C”: Consultation (when only few companies are asked for an offer).