## ZK-04-2010-11, př. 1
Summary Allocation Table | [13 empty] | ZK-04-2010-11, př. 1
Počet stran: 1
Vysocina Regional Infrastructure (Finance Contract B)
Name of Operation:
Number of Operation: |  | 2006-0079
Financial table for all schemes (all in CZK)
Category A)
EIB Project number | Project identification | Name of project | Operational Programme | Priority | Measure | Total costs (CZK) |  | EU contribution (CZK) |  | Region's contribution (CZK) |  | Other resources (CZK) |  | Implementation Start of works End of works
(use numbering in chronological order) | (national system code) |  | (use abbreviations and/or numbering with explanatory notes below) |  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan Actual (DD/MM/YYYY) |  | Plan Actual (DD/MM/YYYY)
1 |  | Pavilón urgentní a intenzivní péče | ROP | 3. | 4. | 357500000 | - | 143000000 | - | 214500000 | - | 0 | - | 2011-01-01 | - | 2012-06-30 | -
2 | CZ.1.11/3.4.00/02.00599 | Pavilón pro matku a dítě | ROP | 3. | 4. | 327036000 | - | 107189000 | - | 219847000 | - | 0 | - | 06/05/2009 | - | 31/05/2011 | -
Category A - Total | [5 empty] | 684536000 | - | 250189000 | - | 434347000 | - | 0 | -
[9 empty] | of that EIB loan | 434347000 | -
Category B)
Project number | Project identification | Name of project | Investment programme (national / regional / other) |  |  | Total costs (CZK) |  | EU contribution (CZK) |  | Region's contribution (CZK) |  | Other resources (CZK) |  | Implementation Start of works End of works
(use numbering in chronological order) | (national system code) |  | (use abbreviations and with explanatory notes below) |  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan Actual (DD/MM/YYYY) |  | Plan Actual (DD/MM/YYYY)
3 |  | Gymnázium Chotěboř | regional budget |  |  | 82156635 | - | - | - | 82156635 | - | 0 | - | 10/08/2009 | - | 30/09/2010 | -
4 |  | SŠ řemesel a služeb MB | regional budget |  |  | 21950000 | - | - | - | 21950000 | - | 0 | - | 01/07/2010 | - | 15/12/2010 | -
5 |  | Rekonstrukce Helenín | regional budget |  |  | 165700000 | - | - | - | 165700000 | - | 0 | - | 05/2011 | - | 11/2012 | -
6 |  | III/03811 Havlíčkův Brod most ev. č. 03811-1 | regional budget |  |  | 28500000 | - | - | - | 28500000 | - | 0 | - | 19/04/2010 | - | 2010-10-30 | -
7 |  | II/344 Dolní Krupá | regional budget |  |  | 27610000 | - | - | - | 27610000 | - | 0 | - | 07/2010 | - | 06/2011 | -
Category B - Total | [5 empty] | 325916635 | - | - | - | 325916635 |  | 0
[9 empty] | of that EIB loan | 271597196 | -